## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Foundations and Prerequistes for doing the project | MUST HAVE | Python, Database,Auth | Gurram Meenakshi | 3- Completed
S2 | S2 | US-002 | Project Understanding, Setup, project achitecture and Google sheet Integration | MUST HAVE | Python, Database,Google,Auth | Gurram Meenakshi | 3- Completed
S3 | S3 | US-003 | Social Media Integration, Content Creation, Optimization | SHOULD HAVE | API,Python,Auth | Gurram Meenakshi | 3- Completed
S4 | S4 | US-004 | Sentiment Analysis, Slack Integration and deployment | SHOULD HAVE | NLP,Python,Slack-API | Gurram Meenakshi | 3- Completed
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
du
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Foundation and prerequistes for doing the project | 23rd Sep | 7th Oct | Gurram Meenakshi | Learnt python basics for the Project | Done |  | Introduction | learned how to install python and jupyter | Learned Naming Conventions in Python | Learned Data Types in Python | Practiced basic programs for better understanding | Practiced different data types and practiced examples | Learned Flow Controls in python | Learned Strings in python | Revised Flow Controls clearly | Practiced Strings in python like creating,accessing,etc... | Revised Strings and started Functions Topic | Practiced types of Functions clearly | Practiced Example programmes on all the topics which are covered | Learned Functions clearly
US-002 | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | Gurram Meenakshi | Understood Project goals,setup, and architecture structure and Google Sheet Integration | Done |  | Understood about OOPs | Understood Packages in python | Understood About NLP Introduction and Text Handling | Understood SPACY Libraries | Practiced what the SPACY Libraries clearly | Understood about Project | Gave explination about project | Understood how to Install Virtual Environment | Understood about Hugging face Transformers | I Explained what I understood about the project | Practiced Hugging Face Transformers | Practiced OOPs concept | Revised NLP clearly | Done with google sheet integration
US-003 | 3 | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th Nov | Gurram Meenakshi | Learned social media API integration and effective content generation techniques | Done |  | Understood API Integration with twitter | Hands on Twitter API Integration | Collected API keys for Instagram and Facebook | Collected API keys and tokens in linkedin | Revision and Interactive session | Practiced API Integration | Understood about Mock Data Generation | Understood about how to Create content and Groq API | Understood about gsheet_connector | Understood about LLM | Revised LLM | Interactive Session | Understood about How to generate different versions of Content | Practiced different content generations
US-004 | 4 | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | Gurram Meenakshi | Learned Sentiment Analysis, Slack Integration and deployment on streamlit | Done |  | Learnt about Application Programming Interface | Clearly understood about API | Revised API topic clearly | Worked on assignment | Interactive session | Understood about Content Optimization | Understood about Sentiment Analysis | Understood about Slack Integration | Understood about A/B testing | Revised A/B testing | Revised and Practiced Sentiment Analysis | Understood about Project Workflow | Discussed about Project Presentation | Mock presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding complete project requirements and end-to-end workflow | Conducted mentor explanation session + reviewed documentation
Sprint 1 | Day 5 | Confusion in Python fundamentals while practicing | Revisited topics and practiced additional programs
Sprint 2 | Day 8 | Challenge in correctly mapping Google Sheets with the project | Re-checked credentials & used proper API token mapping with mentor assistance
Sprint 2 | Day 10 | Difficulty understanding OOPS + Module imports for project structure | Watched tutorials + mentor support + hands-on practice
Sprint 2 | Day13 | Environment setup issues (Virtual environment + installation errors) | Re-installed dependencies & verified installation using mentor guidance
Sprint 3 | Day 16 | Twitter / social media API integration issues (Auth failure) | Updated keys & corrected API endpoint calls
Sprint 3 | Day 18 | Groq API credential errors | Requested new API key and corrected environment variables
Sprint 3 | Day 20 | Difficulty generating multiple content variations automatically | Implemented fallback mechanism + prompt improvements
Sprint 4 | Day 24 | Sentiment analysis results inconsistent → classification confusion | Validated results using additional datasets & mentor guidance
Sprint 4 | Day 26 | Slack message push not working initially | Updated correct webhook and verified connection
Sprint 4 | Day 28 | Streamlit deployment blank page | Debugged layout errors & re-ran server + fixed imports
Sprint 4 | Day 29 | A/B Testing “recommended” key error → app crash | Fixed code logic + added default return values
Sprint 4 | Day 30 | Google Sheets logs not visible due to connectivity timeout | Added retry handling + verified internet permissions

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-25 | 2025-10-07 | Gurram Meenakshi | Practicing Python fundamentals with coding tasks | Just reading theory without hands-on | Revision after each concept | Completed Python basics (variables, strings, loops, functions) and built small practice programs
2 | Sprint 2 | 2025-10-08 | 2025-10-22 | Gurram Meenakshi | Setting up APIs and the project environment properly | Delaying environment setup and integrations | Clarifying doubts with mentor | Integrated Google Sheets with API credentials and set up the project structure successfully
3 | Sprint 3 | 2025-10-23 | 2025-11-06 | Gurram Meenakshi | Working on social media integration and content generation | Trying to test everything manually first | Improving content generation features with Groq/Gemini | Successfully implemented Twitter API posting, created content variations, and tested automation for posting
4 | Sprint 4 | 2025-11-07 | 2025-11-24 | Gurram Meenakshi | Performing Sentiment Analysis, A/B Testing, and Slack notifications | Ignoring minor backend errors during testing | Improve UI and execution flow with Streamlit | Integrated sentiment engine, A/B test comparison, Slack alerts & executed full pipeline end-to-end